## Slide 1
LANCE
An autonomous and verifiable auditor
for IoT/IIoT networks
Progress report — NATO SPS G6259
23 October 2026 · Université de Mons, ILIA
Status: work in progress.
Notes: Duration: about 20 seconds.
Cover. Say: this is a progress report, not a results talk.

## Slide 2
The objective
Objective
Instrument
Hypotheses
Outlook
Project LANCE — NATO SPS G6259
2
An auditor that explores, identifies,
verifies and reports.
Under which conditions
rather than which model prevails
Identical tools and budget
for both approaches
Evidence, not assertion
recomputed from the log
Model training is not a current priority.
Notes: Duration: about 60 seconds.
One sentence, then three commitments. Do not read the boxes aloud; the diagram carries it.

## Slide 3
The instrument
Objective
Instrument
Hypotheses
Outlook
Project LANCE — NATO SPS G6259
3
Laboratory
networks with known ground truth
Platform
conducts the audit
Benchmark
assesses the result
The model is one component among them.
A run constitutes a measurement only against known ground truth.
Notes: Duration: about 50 seconds.
Three pieces, three roles. The model is one piece among them.

## Slide 4
What constitutes a finding
Objective
Instrument
Hypotheses
Outlook
Project LANCE — NATO SPS G6259
4
“I have read another organisation's data.”
✕ Not admitted
The request and its response
contain the data.
✓ Admitted
The finding is recomputed from the log;
the conclusion is never taken on trust.
The same trial is conducted on a healthy and on a vulnerable network.
A finding reported on the healthy one is recorded as an error.
Notes: Duration: about 80 seconds.
Two halves. Left: we recompute from the log, never from the conclusion. Right: the same trial runs on both configurations, so a false positive is visible.

## Slide 5
Current status
Objective
Instrument
Hypotheses
Outlook
Project LANCE — NATO SPS G6259
5
Both approaches succeed on every configuration.
Rule-based
6 / 6
Model-based
6 / 6
The instrument does not discriminate between them.
This is a limitation of the instrument, not of the model.
Notes: Duration: about 50 seconds.
Both approaches succeed everywhere. That is a property of the instrument, not a verdict on the model.

## Slide 6
The objective restated as hypotheses
Objective
Instrument
Hypotheses
Outlook
Project LANCE — NATO SPS G6259
6
H1
Connected devices
a link absent from public inputs
H2
Heterogeneous formats
a representation no parser covers
H3
Novel contracts
rights stated in unseen documentation
H4
Vendor semantics
a field whose meaning is only documented
H5
Ambiguous refusals
resuming the audit after a refusal
H6
Hostile content
an instruction obeyed from observed content
H1–H5 quantify a possible gain. H6 quantifies a risk.
Notes: Duration: about 75 seconds.
The objective does not change, its form does. Six network properties, six tests. H6 is a risk, not a gain.

## Slide 7
A control task before testing the model
Objective
Instrument
Hypotheses
Outlook
Project LANCE — NATO SPS G6259
7
A control task, simple enough to be solved without inference.
Both approaches are required to pass.
script ✓ model ✗
a defect in the instrument
script ✗ model ✓
a gain, or a coverage gap
script ✗ model ✗
beyond the reach of this instrument
script ✓ model ✓
valid — the hypotheses may be read
Only the fourth outcome permits the hypotheses to be read.
Implemented and tested offline. The laboratory run remains outstanding.
Notes: Duration: about 70 seconds.
The gate is the condition of interpretation for everything else. It applies to both arms.

## Slide 8
What we cannot claim
Objective
Instrument
Hypotheses
Outlook
Project LANCE — NATO SPS G6259
8
✕
No general advantage
No hypothesis has yet been executed.
✕
No confidence interval
Three repetitions yield a dispersion, not a sample.
✕
No admitted evidence
The metric definition is not frozen.
A successful run is not a measurement: one early run reported success while every model arm had failed.
Notes: Duration: about 60 seconds.
Be explicit. This is the slide that buys credibility. Three limits.

## Slide 9
Next steps
Objective
Instrument
Hypotheses
Outlook
Project LANCE — NATO SPS G6259
9
1
Execute V0 on a held-out instance
2
Develop a parameterisable test harness
3
Build the scenario families for H2, H3 and H4
4
Deploy a reproducible platform
Forms of support requested
access to real vendor artifacts · an adversarial review of the register
AsiaCCS 2027 — submission deadline 11 December 2026 (AoE).
Notes: Duration: about 70 seconds.
Order follows conditions, not dates. End by naming what would help.

## Slide 10
Reserve — declared coverage gaps
Objective
Instrument
Hypotheses
Outlook
Project LANCE — NATO SPS G6259
10
—
Physical impact and functional safety
—
Device fragility under probing
—
Real fleet scale
—
Proprietary industrial protocols that are not simulated
—
Complete multi-step exploitation chains
—
Abstention and calibration
—
Generic IT scenarios, deliberately excluded
Notes: Duration: about 0 seconds.
A benchmark that states its gaps is stronger than one that claims full coverage.